## Cover
TUSCANY VILLAGE SELF STORAGE
User Acceptance Testing (UAT) Plan & Test Cases
Project Information
Project Name | Tuscany Village Self Storage — Management Platform
Document Type | User Acceptance Testing (UAT) Plan
Document Version | 1.0
Release / Build | Production candidate
Prepared By | Hive Media Studio
Prepared For | David (Tuscany Village Self Storage)
Date Issued | 2026-06-02
Production URL | https://tuscany-storage.onrender.com
Repository | github.com/Shiru04/tuscany-storage
Test Environment | Staging — production-equivalent data
Browser Support | Chrome (latest), Safari (latest), Edge (latest), Firefox (latest)
Mobile Support | iOS Safari, Android Chrome (responsive)
Final Acceptance Sign-Off
Role | Name | Signature | Date
Client / Product Owner
Project Manager
QA Lead
Technical Lead

## Instructions
How to Use This Document
This workbook contains the User Acceptance Test (UAT) cases for Tuscany Village Self Storage. Its purpose is to verify, prior to production release, that every user-facing feature behaves as expected from the perspective of the end user (Admin, Tenant, Public visitor). Each test case below describes a scenario, the exact steps to reproduce, and the expected outcome. The tester executes each case and records the result.
Testing Workflow
1. Open the 'Test Environment' tab and confirm test credentials and URLs are accessible.
2. Open the 'Test Cases' tab. Filter by module if you want to focus on one area.
3. For each test case: read Preconditions, execute the Steps, compare against Expected Result.
4. Record what actually happened in 'Actual Result' and select a Status from the dropdown.
5. If Status = Fail or Blocked: open the 'Defect Log' tab and create an entry. Reference its Defect ID back in the test case row.
6. Fill in Tester Name and Test Date for every case you execute.
7. The 'Summary' tab automatically counts results — no manual update needed.
8. When all Critical and High cases pass, parties sign the 'Cover' tab to release the build to production.
Status Definitions
Status | Meaning
Not Run | Test has not been executed yet (default state).
Pass | Actual result matches expected result. No defect.
Fail | Actual result does not match expected result. A defect must be raised.
Blocked | Test cannot be executed because of an environmental issue or dependency on a failed earlier test.
N/A | Test is not applicable to this release (feature disabled, deferred, etc.). Add reason in Comments.
Defect Severity Definitions
Severity | Meaning
Critical | Blocks core business operation. No workaround. Examples: cannot log in, payments fail across the board, gate access broken for all tenants.
High | Major function broken or significantly degraded. Workaround exists but is painful. Must be fixed before release.
Medium | Feature partially works or has noticeable defect that does not block primary flow. Should be fixed soon.
Low | Cosmetic issue, minor inconvenience, or edge case. Can be deferred.
Test Case Priority
Priority | Meaning
Critical | Must pass for release. Covers core business functions (auth, payment, gate access, move-in).
High | Must pass for release. Covers major features users rely on daily.
Medium | Should pass. Covers secondary flows. Failures discussed before release.
Low | Nice to have. Edge cases, cosmetics, rare flows.
Release / Sign-Off Criteria
• 100% of Critical-priority test cases have Status = Pass.
• ≥ 95% of High-priority test cases have Status = Pass.
• No open defects with Severity = Critical or High.
• All Critical / High defects raised during testing are either Fixed-Verified or Accepted-with-Workaround.
• All sign-off rows on the Cover sheet are completed.

## Test Environment
Test Environment & Credentials
URLs
Production | https://tuscany-storage.onrender.com
Admin Login | https://tuscany-storage.onrender.com/login
Tenant Portal | https://tuscany-storage.onrender.com/portal
Public Site | https://tuscany-storage.onrender.com
Reserve Unit (Move-In Funnel) | https://tuscany-storage.onrender.com/reserve
Test Credentials
Role | Email / Username | Password | Notes
Admin | admin@tuscanystorage.com | (provided separately) | Full admin access
Tenant 1 | john@example.com | tenant123 | Active tenant with unit + autopay on
Tenant 2 | jane@example.com | tenant123 | Active tenant with balance owed
Tenant 3 | bob@example.com | tenant123 | Delinquent tenant (for lockout tests)
Stripe Test Cards (TEST mode only)
Card Number | Expected Behaviour | Notes (use any future expiry, any CVC, any ZIP)
4242 4242 4242 4242 | Successful charge | Default success card.
4000 0025 0000 3155 | Requires 3D Secure | Tests Strong Customer Authentication challenge.
4000 0000 0000 9995 | Decline — insufficient funds | Used for decline-handling tests.
4000 0000 0000 0002 | Decline — generic | Generic decline.
4000 0000 0000 0341 | Attach succeeds, future charge fails | Use for autopay failure tests.
Tester Prerequisites
• Working email inbox for receiving test confirmations and receipts (e.g., +uat alias on a real address).
• Mobile phone capable of receiving SMS (for text-to-open and SMS notification tests).
• Modern browser (Chrome / Edge / Safari latest).
• Access to the staging environment URL above.
• Stripe test cards listed in this sheet — do NOT use real credit cards.
• (For PDK / gate tests) coordination with the on-site PDK device, or use of the sandbox simulator.

## Test Cases
Test ID | Module | Sub-Module | Priority | Test Title | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Tester | Test Date | Comments | Defect ID
AUTH-001 | Authentication | Login | Critical | Admin can log in with valid credentials | Admin account exists. | 1. Navigate to /login. 2. Enter admin email and password. 3. Click Sign In. | admin@tuscanystorage.com / valid password | User is redirected to /admin dashboard. Sidebar nav is visible. Session is established. |  | Not Run
AUTH-002 | Authentication | Login | Critical | Tenant can log in and lands on portal | Tenant account exists with assigned unit. | 1. Navigate to /login. 2. Enter tenant email + password. 3. Click Sign In. | john@example.com / tenant123 | User is redirected to /portal. Dashboard shows tenant's name, balance, and rentals. |  | Not Run
AUTH-003 | Authentication | Login | High | Login fails with wrong password | Tenant account exists. | 1. Navigate to /login. 2. Enter valid email + wrong password. 3. Click Sign In. | john@example.com / WrongPass | Error message displayed (generic 'invalid credentials'). User stays on login page. No session created. |  | Not Run
AUTH-004 | Authentication | Login | Medium | Login fails with non-existent email | — | 1. Navigate to /login. 2. Enter random email + any password. 3. Click Sign In. | noone@example.com / anything | Same generic error as wrong password (no enumeration of valid emails). |  | Not Run
AUTH-005 | Authentication | Password reset | High | Tenant can request password reset | Tenant account exists. | 1. Click 'Forgot Password' on login screen. 2. Enter tenant email. 3. Click Send. | john@example.com | Confirmation screen shown. Reset email arrives at inbox within 2 minutes with reset link. |  | Not Run
AUTH-006 | Authentication | Password reset | High | Reset link sets a new password | Reset email received within last 24h. | 1. Open the reset link. 2. Enter new password (meets strength rules) twice. 3. Submit. 4. Log in with the new password. | Strong new password (e.g., Tuscany!2026) | Password is updated. Login with new password succeeds. Login with old password fails. |  | Not Run
AUTH-007 | Authentication | Password reset | Medium | Reset link expires after use | Password just reset using a link. | 1. Open the same reset link a second time. | — | Link is rejected. Page shows 'link expired/invalid' message. |  | Not Run
AUTH-008 | Authentication | Logout | High | User can log out and session ends | Logged in as any role. | 1. Click user menu in top-right. 2. Click Sign Out. 3. Try to navigate to /admin or /portal. | — | Redirected to /login. Protected pages redirect to login when accessed. |  | Not Run
AUTH-009 | Authentication | Session | Medium | Admin route blocks tenant role | Logged in as tenant. | 1. While logged in as tenant, navigate directly to /admin in URL bar. | — | Tenant is redirected away (to /portal or /login). No admin content rendered. |  | Not Run
PUB-001 | Public Site | Home | Medium | Public homepage loads and displays facility info | — | 1. Open the production URL in a fresh browser. | — | Homepage loads. Facility name, hero copy, and CTA buttons are visible. No JS errors in console. |  | Not Run
PUB-002 | Public Site | Units listing | High | Available units are displayed publicly | At least one unit has status = available. | 1. From homepage, click 'Units' or 'Reserve'. 2. Browse the unit grid. | — | Units shown with size, monthly price, features. Filters by size work. Sold-out / occupied units do not appear as available. |  | Not Run
PUB-003 | Public Site | Size guide | Low | Size guide page renders | — | 1. Navigate to /size-guide. | — | Visual comparisons for 5x5, 5x10, 10x10, 10x15, 10x20 displayed. Page is responsive on mobile. |  | Not Run
PUB-004 | Public Site | Contact form | High | Visitor can submit contact form | — | 1. Navigate to /contact. 2. Fill name, email, subject, message. 3. Submit. | Use a real reachable email | Success confirmation displayed. Admin receives notification email. Submission appears in /admin/site-forms. |  | Not Run
PUB-005 | Public Site | Waiting list | High | Visitor can join waiting list for a size | — | 1. Navigate to /waiting-list. 2. Fill form (name, email, phone, requested size, notes). 3. Complete captcha. 4. Submit. | Valid contact info | Confirmation shown. Entry appears in /admin/waiting-list. Confirmation email received. |  | Not Run
PUB-006 | Public Site | Blog | Low | Blog posts list and detail render | At least one post is published. | 1. Navigate to /blog. 2. Click a post. | — | Posts listed with title and excerpt. Detail page shows full post content. |  | Not Run
MOV-001 | Move-In | Funnel | Critical | New tenant completes full move-in (happy path) | Unit available. Tester has a working email + Stripe test card. | 1. From /units pick a unit, click Reserve. 2. Step 1 contact info: fill name/email/phone/address + SMS consent. 3. Step 2 personal info: DL, employer, emergency contact, etc. 4. Step 3 alternate contact (optional). 5. Step 4 billing info: Stripe card. 6. Step 5 review agreement, e-sign, accept terms. 7. Submit. | Test card 4242 4242 4242 4242 / 12/30 / 123 / 12345 | Reservation succeeds. Tenant + Lease are created. Gate code is auto-assigned. Welcome email with login credentials received. Tenant is redirected to /portal with welcome modal. |  | Not Run
MOV-002 | Move-In | Validation | High | Move-in form blocks missing required fields | — | 1. Start move-in flow. 2. On Step 1, click Next without filling any required field. | — | Form does not advance. Each required field shows an inline validation message. |  | Not Run
MOV-003 | Move-In | Validation | High | Move-in form rejects invalid email format | — | 1. On Step 1, fill name + phone, enter 'not-an-email' in email field. 2. Try to advance. | — | Email field shows format-error. Cannot advance. |  | Not Run
MOV-004 | Move-In | Payment | Critical | Move-in is rejected when card is declined | Unit available. | 1. Complete steps 1–4 of move-in. 2. Use decline test card on billing step. 3. Submit. | Test card 4000 0000 0000 0002 | Payment fails with clear error. Tenant is NOT created. Lease is NOT created. No gate code issued. User can retry with different card. |  | Not Run
MOV-005 | Move-In | Agreement | High | Tenant can e-sign agreement during move-in | On the e-sign step of move-in flow. | 1. Draw or type signature. 2. Tick the 'I agree' checkbox. 3. Submit. | — | Signature is captured. Agreement is marked signed. PDF of signed agreement available in tenant portal. |  | Not Run
MOV-006 | Move-In | Reservation fee | Medium | Reservation fee is charged when configured | Reservation fee for that unit type is configured > $0 in Settings. | 1. Complete a move-in for a unit type that has a reservation fee. | Reservation fee = $25 (example) | Reservation fee appears in pricing summary on the final step. Tenant is charged at submission (or added to first invoice, per facility setting). |  | Not Run
MOV-007 | Move-In | Welcome | Medium | Welcome modal appears on tenant's first portal visit | Tenant just completed move-in. | 1. After move-in submission, observe portal first-load. | — | Modal appears with welcome message and instructions. Modal can be dismissed and does not re-appear on next login. |  | Not Run
POR-001 | Tenant Portal | Dashboard | Critical | Tenant dashboard shows correct balance and rentals | Tenant is logged in with active lease and known balance. | 1. Navigate to /portal. | — | Dashboard displays tenant name, unit(s) with size/rate/next-bill-date, current balance, next-bill date, deposit, agreement-signed status. |  | Not Run
POR-002 | Tenant Portal | Profile | High | Tenant can update profile when enabled | Setting customersCanEditProfile = true. Logged in as tenant. | 1. Navigate to /portal/profile. 2. Change phone number. 3. Save. | Any new valid phone number | Update succeeds. Reload shows new value. Admin tenant detail page reflects the new phone. |  | Not Run
POR-003 | Tenant Portal | Profile | Medium | Profile edit hidden when disabled | Setting customersCanEditProfile = false. | 1. Navigate to /portal/profile as tenant. | — | Profile fields are read-only. No Save button visible. |  | Not Run
POR-004 | Tenant Portal | Billing | High | Tenant can add a payment method | Tenant has no card on file. | 1. Navigate to /portal/billing. 2. Click Add Card. 3. Enter Stripe test card. 4. Save. | Test card 4242 4242 4242 4242 | Card is saved. Last 4 digits and expiry are displayed on /portal/billing. Stripe Dashboard reflects new payment method on this customer. |  | Not Run
POR-005 | Tenant Portal | Billing | High | Tenant can replace existing card | Tenant already has a card on file. | 1. Navigate to /portal/billing. 2. Click Update Card. 3. Enter new test card. 4. Save. | Test card 4000 0025 0000 3155 | Old card is replaced. New card last 4 / expiry are displayed. Stripe customer's default payment method is updated. |  | Not Run
POR-006 | Tenant Portal | Billing | High | Tenant can toggle autopay on/off | Logged in as tenant with card on file. | 1. Navigate to /portal/billing. 2. Toggle autopay on (then off). 3. Reload. | — | Toggle persists. Admin tenant page shows correct autopay status. |  | Not Run
POR-007 | Tenant Portal | Payments | Critical | Tenant can make a one-time payment | Tenant has an outstanding balance and a saved card. | 1. Navigate to /portal/payments/new. 2. Choose 'Pay full balance' (or custom amount). 3. Select saved card. 4. Submit. | — | Payment succeeds. Balance updates to $0 (or reduced). Receipt email is received. Payment appears in history. |  | Not Run
POR-008 | Tenant Portal | Payments | High | Payment with 3D Secure card triggers SCA challenge | Tenant has outstanding balance. | 1. Make a payment using the 3DS-required test card. | Card 4000 0025 0000 3155 | 3D Secure popup/redirect appears. After completing challenge, payment succeeds. |  | Not Run
POR-009 | Tenant Portal | Payments | High | Failed payment is recorded and surfaces to tenant | Tenant has outstanding balance. | 1. Make a payment using the decline card. | Card 4000 0000 0000 0002 | Clear error message shown. Balance does not change. Failed payment recorded in admin payments report. |  | Not Run
POR-010 | Tenant Portal | Payments | Medium | Payment history shows all completed payments | Tenant has at least 2 historical payments. | 1. Navigate to /portal/payments. | — | Payment history table lists date, amount, status, and link to receipt for each payment. |  | Not Run
POR-011 | Tenant Portal | Gate code | Critical | Tenant can view their gate code | Logged in as tenant with gate code assigned. | 1. Navigate to /portal/gate-code. 2. Click Reveal. | — | Code is blurred by default. Reveal toggle un-blurs the code. Same code shown as in admin tenant detail. |  | Not Run
POR-012 | Tenant Portal | Gate code | High | Tenant can request a new gate code | Tenant logged in. | 1. Navigate to /portal/gate-code. 2. Click 'Request New Code'. 3. Confirm. | — | New code generated and displayed. SMS with new code received within 2 minutes. Old code no longer works at gate (verify if PDK is live). |  | Not Run
POR-013 | Tenant Portal | Gate access history | Medium | Tenant sees their own access events | Tenant has at least one historical gate entry. | 1. Navigate to /portal/gate-code. 2. Scroll to access history. | — | List shows tenant's entry/exit events with timestamp, gate name, source. Filterable by event type and date range. |  | Not Run
POR-014 | Tenant Portal | Move-out request | High | Tenant can request a move-out date | Logged in as tenant with active lease, setting customersCanScheduleMoveOuts = true. | 1. Navigate to /portal/move-out. 2. Pick lease, date, optional notes. 3. Submit. | Move-out date 7 days from today | Confirmation displayed. Admin sees the request in /admin/move-out as 'pending_moveout'. |  | Not Run
POR-015 | Tenant Portal | Move-out request | Medium | Move-out nav item hidden when disabled | Setting customersCanScheduleMoveOuts = false. | 1. Log in as tenant. 2. Inspect portal sidebar. | — | 'Move Out' item does not appear in the sidebar. Direct URL /portal/move-out returns a friendly disabled message or 404. |  | Not Run
POR-016 | Tenant Portal | Lease | High | Tenant can sign an unsigned lease from portal | Tenant has lease with status active but unsigned. | 1. Navigate to /portal/lease/sign?leaseId=... 2. Draw / type signature. 3. Submit. | — | Signature captured. Lease marked signed. Signed PDF available in /portal/lease and emailed to tenant. |  | Not Run
POR-017 | Tenant Portal | Instructions | Low | Instructions page renders configured content | Settings.newRenterInstructions has content. | 1. Navigate to /portal/instructions. | — | Page shows the formatted instructions from settings. |  | Not Run
ATEN-001 | Admin / Tenants | List | High | Admin sees full tenant list with key columns | Database has tenants. | 1. Log in as admin. 2. Navigate to /admin/tenants. | — | Table loads with name, unit, status, balance, autopay indicator. Pagination works. Search by name returns matches. |  | Not Run
ATEN-002 | Admin / Tenants | Search & filter | Medium | Filter by status returns correct subset | Tenants in multiple statuses exist. | 1. On /admin/tenants apply status filter = 'Delinquent'. | — | Only delinquent tenants are listed. Counter updates. |  | Not Run
ATEN-003 | Admin / Tenants | Detail | High | Tenant detail shows contact, leases, balance, billing history | Open a known tenant. | 1. Click a tenant row. | — | Detail page shows contact info, active leases, balance, recent 10 transactions, autopay status, default card. |  | Not Run
ATEN-004 | Admin / Tenants | Create | High | Admin can create a new tenant manually | — | 1. Click 'New Tenant' on /admin/tenants. 2. Fill all required fields. 3. Save. | Unique email, name, phone | Tenant is created. Confirmation shown. New tenant appears in list. Optional welcome email is sent if enabled. |  | Not Run
ATEN-005 | Admin / Tenants | Edit | Medium | Admin can edit tenant contact info | Open a tenant detail. | 1. Click Edit. 2. Change address. 3. Save. | — | Address updated. Reload confirms change. |  | Not Run
ATEN-006 | Admin / Tenants | Password reset | Medium | Admin can send password reset link to tenant | Open a tenant. | 1. Click 'Send Password Reset'. | — | Confirmation shown. Tenant inbox receives reset email. |  | Not Run
ATEN-007 | Admin / Tenants | Rent unit | Critical | Admin can rent a unit to an existing tenant | Tenant with no active lease exists. Unit with status=available exists. | 1. Open tenant. 2. Click Rent Unit. 3. Select unit. 4. Configure rate, deposit, proration, billing day. 5. Submit. | Available unit, monthly rate $150, billing day 1 | Lease is created. Unit status changes to occupied. First invoice generated. Tenant appears with new unit on portal. |  | Not Run
ATEN-008 | Admin / Tenants | Reserve unit | Medium | Admin can reserve a unit for a tenant | Unit available, reservation fee may be configured. | 1. Open tenant. 2. Reserve Unit → pick unit → set reserve end date → save. | Reserve until 7 days from today | Unit changes to 'reserved'. Reservation fee (if configured) is added to tenant balance. |  | Not Run
ATEN-009 | Admin / Tenants | Gate access | Critical | Admin can regenerate a tenant gate code | Tenant has unit + existing code. | 1. Open tenant Gate Access. 2. Click Regenerate Code. | — | Code changes. Tenant receives SMS notification with new code (if SMS enabled). Old code stops working at gate. |  | Not Run
ATEN-010 | Admin / Tenants | Gate access | High | Admin can manually lock out a tenant | Tenant has active gate access. | 1. Open tenant Gate Access. 2. Set lockout = today, add reason. 3. Save. | Reason: 'UAT — manual lockout' | Tenant status updates to 'Locked Out'. Tenant removed from PDK access group (when PDK enabled). Tenant portal shows locked-out banner. |  | Not Run
ATEN-011 | Admin / Tenants | Gate access | High | Admin can unlock a tenant | Tenant is currently locked out. | 1. Open tenant Gate Access. 2. Click Unlock / clear lockout. | — | Status returns to Active. Gate access restored at PDK. Tenant can use code again. |  | Not Run
ATEN-012 | Admin / Tenants | Make payment | Critical | Admin can charge tenant card off-session | Tenant has card on file. | 1. Open tenant. 2. Click Make Payment. 3. Enter amount + description. 4. Submit. | Amount $50, type rent | Payment succeeds via Stripe. Receipt issued. Balance adjusts. Charge appears in tenant billing history. |  | Not Run
ATEN-013 | Admin / Tenants | Add credit | Medium | Admin can apply a credit to tenant account | Open tenant. | 1. Click Add Credit. 2. Enter amount + reason. 3. Save. | Credit $20, reason 'UAT credit' | Negative charge (credit) appears in billing history. Balance reduces by amount. |  | Not Run
ATEN-014 | Admin / Tenants | Refund | High | Admin can refund a card payment | Tenant has a recent successful card payment. | 1. Open tenant billing history. 2. Click a card payment → Refund. 3. Enter amount + reason. 4. Submit. | Refund $10 of a $50 payment | Stripe refund initiated (verify in Stripe Dashboard). Refund record created. Tenant balance reflects refund. |  | Not Run
ATEN-015 | Admin / Tenants | Recurring fees | Medium | Admin can add a recurring monthly fee to a tenant | Open tenant Recurring Fees page. | 1. New recurring fee → name, amount, due day, auto-charge flag. 2. Save. | $10 Insurance, day 1, auto-charge on | Fee appears in tenant recurring fees list. On the due day, autopay job picks it up and charges if card available. |  | Not Run
ATEN-016 | Admin / Tenants | Letters | Low | Admin can print a late notice for a tenant | Open tenant. | 1. Letters → Late Notice → Print. | — | PDF generated with tenant name, balance, due date, and configured template. |  | Not Run
ATEN-017 | Admin / Tenants | Move-out finalize | Critical | Admin can finalize a move-out and issue receipt | Tenant has pending move-out request. | 1. Open /admin/move-out → tenant. 2. Review final charges. 3. Click Finalize. 4. Send receipt via email. | — | Lease ended. Unit returns to available status. Tenant removed from PDK group. Move-out receipt email received with final settlement. |  | Not Run
ATEN-018 | Admin / Tenants | Duplicates | Low | Duplicate detection lists likely duplicates | At least 2 tenant records share surname/address. | 1. Navigate to /admin/tenants/duplicates. | — | Likely duplicates listed with confidence score. Merge action consolidates the two records. |  | Not Run
AUNI-001 | Admin / Units | List view | High | Unit list loads with status, type, tenant, rate | Units exist in DB. | 1. Navigate to /admin/units/list. | — | Table shows columns and supports sorting by number/rate. Filters by type and status work. |  | Not Run
AUNI-002 | Admin / Units | Site map | Medium | Site map renders units with status colours | Units exist with floor layout. | 1. Navigate to /admin/units/site-map. | — | Visual layout displays units coloured by status (available, occupied, reserved, down). Clicking a unit opens its detail. |  | Not Run
AUNI-003 | Admin / Units | Create | High | Admin can create a new unit | — | 1. Click New Unit. 2. Fill number, type, size, floor, price, features. 3. Save. | Unit 999, 10x10, climate-controlled, $150/mo | Unit is created. Appears in list and on site map. |  | Not Run
AUNI-004 | Admin / Units | Edit | Medium | Admin can edit unit price and features | Open a unit detail. | 1. Click Edit. 2. Change street price. 3. Save. | New price $175 | Update persists. Listing reflects new rate. |  | Not Run
AUNI-005 | Admin / Units | Maintenance | Medium | Admin can mark unit down for maintenance | Open an available unit. | 1. Set status = Down. 2. Save. | — | Unit removed from public availability. Status shown as Down in admin views. |  | Not Run
APAY-001 | Admin / Payments | List | High | Payments list shows all transactions | Payments exist. | 1. Navigate to /admin/payments. | — | Table lists payments with date, tenant, type, status, amount. Filters by date range and status work. |  | Not Run
APAY-002 | Admin / Payments | Export | Medium | Admin can export payments to CSV | Payments list loaded with at least one row. | 1. Click Export CSV. | — | CSV download starts. File contains the filtered rows with all visible columns. |  | Not Run
APAY-003 | Admin / Payments | Transaction detail | Medium | Admin can view full payment record | At least one successful card payment exists. | 1. Open a payment row. | — | Detail shows amount, status, Stripe PaymentIntent / Charge ID, line items, and links to refund and resend receipt. |  | Not Run
APAY-004 | Admin / Payments | Resend receipt | Low | Admin can resend a receipt to tenant | Open a payment detail. | 1. Click Resend Receipt. | — | Confirmation displayed. Tenant inbox receives the receipt email. |  | Not Run
ADEL-001 | Admin / Delinquency | Dashboard | High | Delinquency dashboard summarises overdue accounts | At least one delinquent tenant exists. | 1. Navigate to /admin/delinquency. | — | KPIs show counts by stage (Late, Locked Out, Pre-Lien). Table lists tenants with days overdue, balance, last payment, last contact. |  | Not Run
ADEL-002 | Admin / Delinquency | Bulk reminder | Medium | Admin can send reminder email in bulk | Multiple delinquent tenants. | 1. Select 2+ tenants → Send Reminder. | — | Confirmation shown. Email logs recorded. Tenants receive reminder emails. |  | Not Run
ADEL-003 | Admin / Delinquency | Lockout | Critical | Admin can lock out a delinquent tenant | Tenant past due, currently active. | 1. Select tenant → Issue Lockout. 2. Confirm. | — | Tenant status changes to Locked Out. Gate access revoked. Tenant receives lockout notification (per template). |  | Not Run
ADEL-004 | Admin / Delinquency | Release | High | Admin can release a tenant from lockout after payment | Locked-out tenant whose balance is now $0. | 1. Select tenant → Release / Unlock. | — | Status returns to Active. Gate access restored. Tenant can sign in and access portal normally. |  | Not Run
ADEL-005 | Admin / Delinquency | Lien notice | High | Admin can issue lien notice | Tenant locked out for configured days. | 1. Select tenant → Issue Lien. | — | Tenant moves to Pre-Lien stage. Lien notice sent per template. Audit entry recorded. |  | Not Run
ADEL-006 | Admin / Delinquency | Auction schedule | Medium | Admin can schedule an auction date | Tenant in Lien stage. | 1. Select tenant → Schedule Auction → pick date. | Date 14 days out | Auction date recorded. Tenant receives auction notice. Date visible on tenant detail. |  | Not Run
AREP-001 | Admin / Reports | Hub | Medium | Reports hub loads all report categories | — | 1. Navigate to /admin/reports. | — | All report cards/links are present (Accounting, Customers, Payments, Facility). |  | Not Run
AREP-002 | Admin / Reports | Rent roll | High | Rent roll report lists active leases with rates | Active leases exist. | 1. Open Rent Roll report. | — | Report shows unit, tenant, monthly rate, billing day, balance. Total at the bottom matches sum. |  | Not Run
AREP-003 | Admin / Reports | Occupancy | Medium | Occupancy report shows current occupancy % | Units exist in multiple statuses. | 1. Open Occupancy report. | — | Occupancy % shown. Breakdown by unit type listed. |  | Not Run
AREP-004 | Admin / Reports | Gate activity | Critical | Gate activity report lists access events | Recent gate events exist (real or simulated). | 1. Open /admin/reports/gate-activity. 2. Filter date range. | Last 7 days | Events list shows timestamp, tenant or visitor, device, source (keypad, sms, app), result. Visitor pass events show visitor attribution. |  | Not Run
AREP-005 | Admin / Reports | Move-in / move-out | Medium | Move-in/out report lists recent events | Recent move-ins and move-outs exist. | 1. Open the Move In/Out report. | Last 30 days | Move-in rows show tenant, unit, date, lease start. Move-out rows show tenant, unit, date, final balance. |  | Not Run
AREP-006 | Admin / Reports | Failed payments | High | Failed payments report lists declines | At least one failed Stripe charge exists. | 1. Open Failed/Declined Payments report. | — | Declined rows show tenant, attempt date, amount, decline reason. |  | Not Run
AREP-007 | Admin / Reports | Lockouts | Medium | Lockouts report lists lockout events with approval state | At least one lockout event exists. | 1. Open /admin/reports/lock-out. | — | Events list with status (pending/approved/executed) shown. Approval actions function (if approval workflow enabled). |  | Not Run
AREP-008 | Admin / Reports | CSV export | Medium | Reports can be exported to CSV | Any report open with data. | 1. Click Export CSV. | — | Download starts. File matches the visible rows. |  | Not Run
ASET-001 | Admin / Settings | General | High | Admin can edit general settings | Logged in as admin. | 1. Navigate to /admin/settings/general. 2. Edit timezone or date format. 3. Save. | Timezone America/New_York | Change persists. Other pages reflect the new locale settings. |  | Not Run
ASET-002 | Admin / Settings | Facility | High | Admin can edit facility info and access hours | — | 1. /admin/settings/facility. 2. Change access hours and save. | Hours 06:00–22:00 | Change persists. PDK group sync (if enabled) re-pushes the new schedule to entry rule. |  | Not Run
ASET-003 | Admin / Settings | Fees | High | Admin can edit late, NSF, auction fees | — | 1. /admin/settings/fees. 2. Change late fee amount. 3. Save. | Late fee $20 | Change persists. New late fees added by delinquency job use the new amount. |  | Not Run
ASET-004 | Admin / Settings | Rental | Medium | Admin can edit billing cycle anchor | — | 1. /admin/settings/rental. 2. Change anchor to 'signup day'. 3. Save. | — | Change persists. New leases use the new anchor for invoice generation. |  | Not Run
ASET-005 | Admin / Settings | Agreement | Medium | Admin can edit agreement template | — | 1. /admin/settings/agreement. 2. Make a small text change. 3. Save. | — | Change persists. New move-ins display the updated agreement on the e-sign step. |  | Not Run
ASET-006 | Admin / Settings | Agreement | Low | Image upload in agreement editor works (R2) | On agreement editor. | 1. Insert image → upload a JPG. | Any small JPG / PNG | Image uploads to Cloudflare R2. URL becomes accessible. Image renders in saved agreement. |  | Not Run
ASET-007 | Admin / Settings | Form fields | Low | Admin can toggle field visibility on signup form | — | 1. /admin/settings/form-fields. 2. Hide 'Driver's License' from signup. 3. Save. 4. Open public move-in flow. | — | DL field is no longer required on signup. |  | Not Run
ASET-008 | Admin / Settings | Late/Lien | High | Admin can configure escalation days | — | 1. /admin/settings/late-lien. 2. Change 'Days past due → Locked out' to 15. 3. Save. | — | Change persists. Delinquency job uses the new value. |  | Not Run
ASET-009 | Admin / Settings | Communications | Medium | Admin can change from-email and reply-to | — | 1. /admin/communications/settings. 2. Change from-name. 3. Save. 4. Trigger a test email. | — | Updated from-name appears in subsequent emails. |  | Not Run
ACOM-001 | Admin / Communications | Templates list | Medium | Templates page lists system and custom templates | — | 1. /admin/communications/templates. | — | All default templates (receipt, late, lockout, lien, etc.) listed with channel toggles. |  | Not Run
ACOM-002 | Admin / Communications | Template edit | High | Admin can edit a template body and subject | Open the Late Notice template. | 1. Change subject and body. 2. Save. 3. Trigger a late notice. | Use placeholder {{tenantName}} | Change persists. Sent late notice uses the new subject and body, with placeholders expanded. |  | Not Run
ACOM-003 | Admin / Communications | Send custom email | Medium | Admin can send a one-off email to selected tenants | — | 1. /admin/communications/send-email. 2. Select 1-2 tenants. 3. Compose subject + body. 4. Send. | Use tester tenants | Confirmation shown. Tenants receive the email. |  | Not Run
ACOM-004 | Admin / Communications | Print batches | Low | Print batches list shows recent jobs | At least one print batch was generated. | 1. /admin/communications/print-batches. | — | Batches listed with status, date, recipient count. |  | Not Run
ACOM-005 | Admin / Communications | Mailing labels | Low | Admin can generate mailing labels | — | 1. /admin/communications/mailing-labels. 2. Select filter (e.g., all active). 3. Generate PDF. | Avery 5160 | PDF generated with correctly formatted addresses. |  | Not Run
ARTE-001 | Admin / Rate Mgmt | Suggestions | Medium | Rate management surfaces unit-type and rental suggestions | Rate management enabled with rules. Units and leases qualifying for change exist. | 1. /admin/rate-management. | — | Unit-type suggestions and rental suggestions tables populated based on rules. |  | Not Run
ARTE-002 | Admin / Rate Mgmt | Batch submit | High | Admin can submit a batch of rate changes | Suggestions present. | 1. Select 1-2 rentals. 2. Submit. | — | Batch is created. Tenants receive notifications per configured channels. Batch appears in /admin/rate-management/batches. |  | Not Run
ARTE-003 | Admin / Rate Mgmt | Batch execution | High | Rate execution cron applies changes on the scheduled date | Batch item exists with changeDate = today. | 1. Run cron 'rate-execution' (or wait until natural run). | — | Lease monthlyRate updated. Item status = executed. Confirmation email sent. |  | Not Run
ARTE-004 | Admin / Rate Mgmt | Cancel item | Medium | Admin can cancel a pending rate change | Pending rate batch item exists. | 1. Open the batch item → Cancel. | — | Item status = cancelled. Lease rate not changed on the previously scheduled date. |  | Not Run
VIS-001 | Visitor Access | Issue | Critical | Admin can issue a temporary visitor pass | PDK group bootstrap done (or sandbox enabled). | 1. /admin/visitor-access. 2. New pass → name, purpose, duration 1h. 3. Submit. | Name 'Electrician', purpose 'Panel check', duration 1h | Pass created. PIN displayed exactly once in reveal dialog. Pass listed under active. PDK holder provisioned (when sync enabled). |  | Not Run
VIS-002 | Visitor Access | PIN visibility | High | PIN is shown only once and not in subsequent lists | Pass just issued. | 1. Close the reveal dialog. 2. Reload list. | — | PIN no longer visible. Only metadata (name, purpose, validity, status) shown. |  | Not Run
VIS-003 | Visitor Access | Revoke | High | Admin can revoke an active pass | Active visitor pass exists. | 1. Click Revoke on a pass row. 2. Confirm. | — | Pass status changes to revoked. PDK holder disabled / removed from group. PIN no longer opens gate. |  | Not Run
VIS-004 | Visitor Access | Expiration cron | High | Cron expires passes past validUntil | A visitor pass with validUntil 2 minutes in the past exists. | 1. Wait for the next cron run (every ~2 minutes) OR manually trigger the cron endpoint. | — | Pass moves to expired status. expiredAt timestamp set. PDK holder removed. |  | Not Run
VIS-005 | Visitor Access | Filter | Low | Admin can filter list by status | Mix of active, expired, revoked passes. | 1. On /admin/visitor-access change filter to 'Expired'. | — | Only expired passes shown. |  | Not Run
VIS-006 | Visitor Access | Audit | Medium | Pass entries record createdBy / revokedBy | Issued and revoked passes by known admins. | 1. Inspect a pass detail. | — | createdBy = the admin who issued. revokedBy + revokedAt set for revoked passes. |  | Not Run
SMS-001 | Text-to-Open SMS | Whitelist authorised | Critical | Authorised phone unlocks gate via SMS | Twilio webhook URL configured on PDK gate settings. Tester's mobile number added to whitelist. | 1. From whitelisted phone, text ANY message (e.g., 'open') to the facility's Twilio number. | Any short text | Reply received: 'Gate opening.' Within seconds entry devices momentarily unlock (verify physically or in PDK panel). AccessLog entry created with source = 'app' or 'sms' and the phone + device IDs. |  | Not Run
SMS-002 | Text-to-Open SMS | Whitelist rejection | Critical | Non-whitelisted phone is silently rejected | Tester's mobile not on whitelist. | 1. From non-whitelisted phone, text the facility number. | Any text | Reply is a generic non-leaking message (or no acknowledgement). NO gate unlock occurs. Console / server logs show rejection. No AccessLog row created. |  | Not Run
SMS-003 | Text-to-Open SMS | Signature verification | High | Webhook rejects requests with invalid Twilio signature | Tester has access to a webhook tester tool (e.g., curl). | 1. POST to /api/webhooks/twilio/sms with bogus X-Twilio-Signature. | Any payload | Response 401/403. No unlock. No DB write. |  | Not Run
SMS-004 | Text-to-Open SMS | Multi-device fan-out | High | All configured entry devices unlock momentarily | Multiple entry devices configured. | 1. Authorised SMS as above. | — | Each entry device receives the momentary unlock command (verify in PDK panel or AccessLog entries: one row per device unlocked). |  | Not Run
SMS-005 | Text-to-Open SMS | Whitelist edit | Medium | Admin can add/remove numbers in the whitelist | On /admin/settings/gate. | 1. Edit whitelist textarea, add a new number, save. 2. Reload page. | +15551234567 | Saved value is normalised (digits + leading +). Reload shows the updated list. |  | Not Run
PDK-001 | PDK Gate | Kill switch | Critical | All PDK sync paths short-circuit when kill switch is off | PDK_SYNC_ENABLED unset. | 1. Issue / revoke a tenant change. 2. Inspect logs. | — | No outbound HTTP to PDK. Local DB write succeeds. No errors raised. |  | Not Run
PDK-002 | PDK Gate | Holder sync | Critical | Tenant changes sync to PDK when enabled | PDK_SYNC_ENABLED=true with valid credentials. | 1. Regenerate a tenant gate code. | — | PDK holder PIN updated within seconds. Tenant.pdkSyncedAt updated. |  | Not Run
PDK-003 | PDK Gate | Group rules sync | High | Editing access hours updates PDK group rules | — | 1. Settings → Facility → change access hours. 2. Save. | Hours 06:00–22:00 | PDK group entry rule schedule updated to new hours. Exit rule remains 24/7. |  | Not Run
PDK-004 | PDK Gate | Reconcile job | Medium | Reconcile cron repairs drift | Manually disable a tenant in PDK panel. | 1. Trigger /api/cron/pdkReconcile. | — | Job re-enables tenant and re-adds them to entry group. Summary shows {patched: 1}. |  | Not Run
PDK-005 | PDK Gate | Webhook — allowed | Critical | Allowed-entry webhook creates AccessLog row | Webhook URL registered, secret configured. | 1. Trigger a successful gate entry (real device or simulator). | — | AccessLog row created with tenant attribution, device, timestamp, result=allowed. |  | Not Run
PDK-006 | PDK Gate | Webhook — denied | High | Denied entry creates denied AccessLog row | — | 1. Use a disabled credential at a gate. | — | AccessLog row created with result=denied. |  | Not Run
PDK-007 | PDK Gate | Webhook — visitor | High | Visitor PIN entry attributes to visitor pass | Active visitor pass with known PIN. | 1. Enter visitor PIN at a reader. | — | AccessLog row created with visitorAccessId set (tenantId null). Visible in gate-activity report under visitor. |  | Not Run
PAY-001 | Stripe / Payments | Autopay charge | Critical | Autopay cron charges tenant on billing day | Tenant with autopayEnabled=true, valid card, lease billingDay = today. | 1. Trigger autopay cron OR wait for natural run. | — | Payment processed (status=succeeded). Receipt email sent. Balance reduces. Charge appears in payments report. |  | Not Run
PAY-002 | Stripe / Payments | Autopay failure | High | Failed autopay sends failure notification | Tenant with card that triggers failure on future charge. | 1. Trigger autopay cron when due. | Card 4000 0000 0000 0341 | Payment fails. Status=failed. Failed-payment email sent to tenant. Admin sees the failed entry. |  | Not Run
PAY-003 | Stripe / Payments | Refund partial | Medium | Partial refund updates balance correctly | $50 successful payment exists. | 1. Refund $20 of the $50 payment. | — | Stripe refund of $20 issued. Tenant balance reflects the partial refund. |  | Not Run
PAY-004 | Stripe / Payments | Late fee | High | Late fee is added after configured days past due | Delinquent tenant with unpaid invoice older than lateFeeAfterDays. | 1. Run delinquency cron. | — | Late fee charge appears in tenant billing history with type=late_fee. Late notice email sent (per template config). |  | Not Run
PAY-005 | Stripe / Payments | Reservation fee charged at move-in | Medium | Configured reservation fee is included at move-in | Unit type has reservation fee > 0. | 1. Complete public move-in. | — | Reservation fee line item appears on first invoice (or charged at submission, per setting). |  | Not Run
PAY-006 | Stripe / Payments | Multi-unit payment | Medium | Tenant with multiple leases can pay all in one checkout | Tenant has 2 active leases with balances. | 1. /portal/payments/new — select pay multi. 2. Submit. | — | Single Stripe charge processes total. Allocations recorded per lease. |  | Not Run
NTF-001 | Notifications | Welcome email | High | New tenant receives welcome email with credentials | Just completed move-in. | 1. Check the tester's inbox after move-in. | — | Welcome email arrives with portal URL and login credentials. |  | Not Run
NTF-002 | Notifications | Payment receipt | High | Successful payment triggers receipt email | Tenant just made a payment. | 1. Check inbox. | — | Receipt email arrives with amount, date, and payment method last 4. |  | Not Run
NTF-003 | Notifications | Late notice | High | Late notice sent on first overdue day | Tenant with unpaid invoice past lateFeeAfterDays. | 1. Run delinquency cron. | — | Late notice email (and SMS if enabled, and print if enabled) sent. Logged in /admin/communications/templates send history. |  | Not Run
NTF-004 | Notifications | Rate change | Medium | Tenant receives rate-change notification on batch submit | Admin submits a rate change batch including tenant. | 1. Submit batch with email channel. | — | Tenant inbox receives rate change notice with effective date. |  | Not Run
NTF-005 | Notifications | Suppression window | Low | Notifications are suppressed during configured holiday window | Settings configured to suppress 1 day window covering today. | 1. Run delinquency cron during suppression window. | — | No notifications go out for that window. Resumes after window. |  | Not Run
NTF-006 | Notifications | SMS opt-out | Medium | Tenant opt-out blocks SMS notifications | Tenant with smsOptIn=false. | 1. Trigger an SMS-channel notification for the tenant. | — | Email is sent. SMS is NOT sent. |  | Not Run
WAIT-001 | Waiting List | Admin view | Medium | Waiting list entries are visible to admin | Public waitlist submission exists. | 1. Navigate to /admin/waiting-list. | — | Entries listed with name, requested size, status, join date. |  | Not Run
WAIT-002 | Waiting List | Notify | Medium | Admin can notify a waitlist member of availability | Waitlist entry exists. Matching unit available. | 1. Open entry → Notify. | — | Notification email is sent. Entry status changes to notified. |  | Not Run
WAIT-003 | Waiting List | Convert | Medium | Admin can convert waitlist entry to a tenant | Waitlist entry exists. | 1. Open entry → Convert. 2. Fill remaining fields, assign unit, submit. | — | Tenant + lease created from the waitlist data. Entry status = converted. |  | Not Run
MOUT-001 | Move-Out | Tenant request | High | Tenant submits move-out request | Tenant logged in with active lease. | 1. /portal/move-out → pick lease, date, submit. | Move-out 7 days out | Request submitted. Admin notified. Status pending_moveout. |  | Not Run
MOUT-002 | Move-Out | Final settlement | Critical | Admin can finalize and compute final balance | Pending move-out exists. | 1. /admin/move-out → open tenant → review charges → Finalize. | — | Final balance calculated. Receipt generated and emailed. Unit returns to available. Tenant.gate access revoked. |  | Not Run
MOUT-003 | Move-Out | Photo upload | Low | Tenant can upload photos during move-out | On portal move-out screen. | 1. Upload 2 photos. 2. Continue. | Any small JPGs | Upload succeeds. Files visible on admin move-out page. |  | Not Run
MOUT-004 | Move-Out | Refund owed | Medium | Refund-owed move-out routes admin to refund flow | Move-out resulting in negative balance. | 1. Finalize a move-out with credit > charges. | — | Final receipt shows refund owed. Admin can issue refund via standard refund flow. |  | Not Run
RET-001 | Retail | Walk-in sale (cash) | Medium | Admin can ring up a walk-in sale to a non-tenant | At least one product with stock. | 1. /admin/retail → New walk-in sale → select product, qty, cash → submit. | 1x product | Sale recorded. Inventory decremented. Receipt generated. |  | Not Run
RET-002 | Retail | Walk-in sale (card) | Medium | Admin can ring up a walk-in sale to a non-tenant via card | Stripe configured. | 1. Walk-in sale → card → enter test card → submit. | Test card 4242 4242 4242 4242 | Charge succeeds. Receipt generated. Sale appears in retail report. |  | Not Run
RET-003 | Retail | Walk-in to tenant | Medium | Sale to existing tenant adds to their balance | Tenant with active account. | 1. Walk-in tenant sale → pick tenant → product → submit. | Tenant: john@example.com, qty 1 | Charge appears on tenant balance. Inventory decremented. |  | Not Run
RET-004 | Retail | Inventory adjust | Low | Admin can adjust inventory with reason | Existing product. | 1. Adjust inventory → reason 'damage' → -1. | — | Stock decremented. History entry recorded with reason and admin. |  | Not Run
XCUT-001 | Cross-cutting | Mobile portal | High | Tenant portal is usable on mobile | Mobile device or DevTools mobile emulation. | 1. Open /portal on iPhone-size viewport. 2. Navigate dashboard, billing, payments, gate code. | — | Layout adapts. All key actions reachable without horizontal scrolling. Buttons are tap-friendly. |  | Not Run
XCUT-002 | Cross-cutting | Mobile move-in | High | Move-in funnel completes on mobile | Mobile viewport. | 1. Full move-in flow on mobile. | — | All steps complete. Stripe CardElement works on mobile. Signature pad works with touch. |  | Not Run
XCUT-003 | Cross-cutting | Browser support | Medium | Portal and admin work on Safari and Edge | Safari (Mac/iOS) and Edge (Win). | 1. Repeat key flows on each browser. | — | No visual or functional regressions vs Chrome. |  | Not Run
XCUT-004 | Cross-cutting | 404 handling | Low | Unknown URLs show a friendly 404 | — | 1. Open a non-existent URL. | — | 404 page is shown with branding and link back to home. |  | Not Run
XCUT-005 | Cross-cutting | HTTPS only | Medium | Site is served over HTTPS | — | 1. Open production URL. | — | Browser shows secure lock. HTTP requests redirect to HTTPS. |  | Not Run
XCUT-006 | Cross-cutting | Auth on admin APIs | Critical | Admin APIs reject unauthenticated requests | — | 1. Hit /api/admin/tenants without session. | — | 401/403 response. No data leaked. |  | Not Run
XCUT-007 | Cross-cutting | Role check on admin APIs | Critical | Tenant role cannot call admin APIs | Tenant session token. | 1. Call admin API with tenant session. | — | 403 response. No data leaked. |  | Not Run

## Defect Log
Defect ID | Linked Test ID | Module | Title | Severity | Status | Steps to Reproduce | Expected | Actual | Environment / Browser | Reported By | Reported Date | Assigned To | Fix Notes | Verified By | Verified Date
DEF-001
DEF-002
DEF-003
DEF-004
DEF-005
DEF-006
DEF-007
DEF-008
DEF-009
DEF-010
DEF-011
DEF-012
DEF-013
DEF-014
DEF-015
DEF-016
DEF-017
DEF-018
DEF-019
DEF-020
DEF-021
DEF-022
DEF-023
DEF-024
DEF-025
DEF-026
DEF-027
DEF-028
DEF-029
DEF-030

## Summary
Test Execution Summary
Status | Count | % of Total
Not Run
Pass
Fail
Blocked
N/A
TOTAL | 146 | 100%
Priority | Total | Passed | % Pass
Critical
High
Medium
Low
Defect Status | Count
Open
In Progress
Fixed
Verified
Closed
Re-Opened
Wont Fix
Accepted Workaround
Sign-Off Readiness
Critical tests passing (must be 100%)
High tests passing (must be ≥ 95%)
Open Critical/High defects (must be 0)